## Timeline
Working process |  | Delivery |  | TIMELINE {{项目名称}}
过程任务 / 工作推进 |  | 交付 / 确认当天 |  | 12月 | [16 empty] | 1月 | [30 empty] | 2月
|  |  |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [5 empty] | Spring festival | [8 empty] | Week 10
Task Sections | Work Content | Note | Deliver date | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
研究导入 Research Introduction | Kick off meeting | / | {{启动日期}} | Week 3 1: National Holiday; Spring festival 15: National Holiday
| 项目背景资料整理 Internal Materials Review | Existing materials review | {{日期范围}} | bar: Week 2 22 to Week 2 26
| 案头研究 / 趋势扫描 Desk Research / Trend Scan | Academic & market perspective | {{日期范围}} | bar: Week 2 22 to Week 2 26; Week 3 29 to Week 3 30
| 阶段性沟通 Check-in | Key alignment session | {{日期}} | bar: Week 3 31
田野阶段 Fieldwork | 受访者招募 Respondent Recruitment | Keep updating | {{日期范围}} | bar: Week 2 23 to Week 2 26; Week 3 29 to Week 3 31
| 研究设计初稿 Research Guideline V1 | V1 delivery | {{日期}} | bar: Week 2 26
| 研究设计确认 Research Guideline Confirmation | / | {{日期}} | bar: Week 4 5
| 线上生活志 / 数字民族志 Digital Ethnography | Keep updating | {{日期范围}} | bar: Week 4 6 to Week 6 19
| 深访样本选定 Participant Selection | / | {{日期}} | bar: Week 5 14
| 深访研究设计 IDI Guideline | V1 delivery | {{日期}} | bar: Week 5 14
| 深访研究设计确认 IDI Guideline Confirmation | / | {{日期}} | bar: Week 5 16
| 一对一深度访谈 In-depth Interviews | {{城市 / 人群要求}} | {{日期范围}} | bar: Week 6 19 to Week 6 25
分析与报告 Analysis & Report | 资料整理与分析 Material Review & Analysis | / | {{日期范围}} | bar: Week 6 19 to Week 6 23; Week 7 26 to Week 7 30
| Topline 递交 Topline Delivery | Key findings debrief | {{日期}} | bar: Week 7 30
| 报告撰写（PPT） Report Writing | V1 report delivery | {{日期}} | bar: Week 8 2 to Week 8 6; Week 9 9 to Week 9 14
| 报告修改 Report Revision | Further improvement | {{日期范围}} | bar: Week 10 24 to Week 10 28
| 终版报告及汇报 Final Report |  | {{日期范围}}
Highlighted in RED are key milestones